## WIP
¦ 9 Dec - 16 Dec 2025 | GCMC 2026 | Last updated 16 Dec, 00:24 ICT | High
Campaign (group) | Task | PIC | Status | Details
Misc | Guss Program uplift for 2026 intake | Danh - Eden | To Do | Production will start in Jan
RMIT Study Expo | RMIT Study Expo - January campaign assets | Danh | In Progress | 1st batch done, working on Jan. batch
RMIT Study Expo | RMIT Study Expo - printed assets | Danh | In Review | 1st draft sent 10 Dec, waiting for review
RMIT Study Expo | Jan Study Expo TikTok | Eden | To Do | Due 8 Jan
Misc | INTON Christmas and new year design | Danh - Trinh | In Progress | Due 18 Dec
Misc | Christmas and New Year flyer - Sri Lanka | Trinh | To Do | Due 19 Dec
Misc | Uni acronym challenge | Trinh | In Progress | 1/2 videos in review. Due 19 Dec
Misc | Chinese Alumni UGC video - Yiliang Zhang | Tran | In Review | 1st draft sent 2 Dec
Misc | Chinese Alumni UGC video - Yiran Zhou | Tran | In Review | 1st draft sent 15 Dec
Misc | Aussie and international snacks reaction video series | Tran | To Do | Due Jan 12
Misc | Popmart challenge video | Tran | In Progress | Due 19 Dec
Sem 1 2026 | Sem 1 Career Connect TikTok | Eden | In Progress | Due 19 Dec
Sem 1 2026 | Sem 1 PG study tips TikTok | Eden | In Review | Updated on Dec 12
Sem 1 2026 | Sem 1 PG student IVs short - form videos (x3) | Eden | In Review | 1/3 videos sent on Dec 16, waiting for review
Domestic SR Event | Career pathways posters | Joanne | On-hold | Awaiting content
Publications 2027 | Editorial V1.5 edits | Joanne | In Progress
Publications 2027 | Admissions V1 edits | Joanne | In Progress
Publications 2027 | Ranking badge design V2 | Joanne | Done