## Weekly Report
(4-11 Nov 2025) | VN Design Team | Last updated: 11 Nov 2025, 5:00 PM | 85%
Campaign | Task | PIC | Status | Details
Website Redesign | Homepage mockup | Alice | Done | Desktop and mobile versions
Website Redesign | Navigation menu | Bob | In Progress | Implementing responsive menu
Website Redesign | Footer design | Alice | Review | Pending client feedback
Mobile App | UI components | Charlie | Done | Button and input styles
Mobile App | Onboarding flow | Diana | WIP | Screens 1-3 completed
Mobile App | Profile screen | Charlie | To Do | Starting next week
Marketing Campaign | Social media graphics | Eve | Done | Instagram and Facebook posts
Marketing Campaign | Email template | Eve | Review | Waiting for approval
Branding | Logo variations | Frank | Blocked | Waiting for brand guidelines
Branding | Color palette | Frank | Done | Primary and secondary colors defined