## WIP
4-11 Nov 2026 | GCMC Design team weeky WIP | Last updated 1 Nov, 15:00 | Extreme
Campaign (group) | Task | PIC | Status | Details
COP 7777 | COP mailout | Joanne | In progress | due 30 Oct
COP 7777 | Short-form videos x4 | Eden | In Review | 4 videos all done, sent FA
COP 7777 | Digital Display Phase 1 | Eden | In Review | 50% approved, 50% in review, working on Phase 2, this is also test how much the text is flowing. Normally this wouldn't be this long
COP 7777 | VTAC, PMAX banners | Eden | Done | WF/FA sent
COP 7777 | Tiktok video refresh | Eden | In progress | WIP, due Nov 7
COP 7777 | COP animation promo asset | Eden | Done | WF/FA sent
COP 7777 | EDM banners phase 2 | Tran | Done | In Review, due 31 Oct
COP 7777 | COP 2025 DIrect Mail design | Danh | In Review | Physical proof review in progress
COP 7777 | Youtube videos | Danh | In progress | 30s video sent on 29 Oct, others due 31 Oct
COP 7777 | COP Parents TikTok | Trinh | In progress | Due 3 Nov
Domestic SR Event | Career pathways posters | Joanne | On-hold | Awaiting content
DSC info day | DSC videos x3 | Tran | Done | All assets updated on 28 Oct
DSC info day | DSC static x4 | Trinh | In Review | Sent 27 Oct, in review
INTON H2 generic ads | Generic ads: 6 x China videos | Tran | Done | Updated on 22 Oct
INTON H2 generic ads | Generic ads: 6 x ISC videos | Trinh | Done | Updated on 23 Oct
INTON SR China week | Pull up banners for DSC x4 | Joanne | In Review | due 28 Oct