## WIP
¦ 27 Jan - 3 Feb 2026 | Welcome, Tuyet · GCMC Weekly Report | Last updated 3 Feb, 14:00 ICT | High
Campaign (group) | Task | PIC | Status | Details
INTON Holidays assets | INTON Valentine / New year assets | Danh | To Do | Due 9 Feb
H1 Domestic | SR H1 Update (edit) Vietnam video | Danh | Done | Approved on 2 Feb
RMIT Study Expo | RMIT Study Expo - printed assets | Danh | In Progress | Final revision in progress
H1 Domestic | Guss Program uplift for 2026 intake | Danh - Eden | Done | Approved on 2 Feb
H1 Domestic | H1 Domestic Flashtalking 300 programs | Danh | In Progress | Due EO Feb 2026
Comms Holdays assets | Lunar New Year eDM GIF | Danh | In Review | Updated on Feb 2, waiting approval
RMIT Trades Event | RMIT Trades Event - maps and design assets | Eden | To Do | In progress, due 6 Feb
H1 / H2 COP | COP video endframe update | Eden | Done | Done, FA/WF sent 30 Jan
Comms Holdays assets | Eid al Fitr 2026 eDM | Eden | In Progress | Due 27 Feb
Misc | SR H1 Career Practitioner Seminar 2026 | Eden | In Progress | In progress, some assets pending (waiting for info)
Comms Holdays assets | Holi 2026 eDM | Tran | To Do | Updated on 2 Feb, due 6 Feb
INTON Holidays assets | INTON New year assets | Tran | In Progress | Due 9 Feb
H1 2026 INTON Always On | H1 2026 Indonesia Always On – META & TIKTOK | Tran | In Progress | Due 10 Feb
Misc | x4 Aussie and international snacks reaction videos | Tran | In Review | All assets updated on 19 Jan
H1 / H2 COP | Short-form video endframe update #2 | Tran | In Review | Updated on 27 Jan
Misc | Popmart challenge video | Tran | In Review | Updated on 2 Feb
INTON Holidays assets | INTON Valentine assets | Trinh | In Progress | Due 9 Feb
H1 2026 INTON Always On | H1 2026 China Always On - videos | Trinh | In Progress | Due 10 Feb
Comms Holdays assets | Ramadan Mubarak eDM | Trinh | In Progress | Revision in progress, due 6 Feb
Misc | Uni acronym challenge | Trinh | In Progress | Awaiting approval / review, due 6 Feb
H1 2026 INTON Always On | H1 2026 China Always On - Static x5 | Tuyet | To Do | Due 10 Feb
INTON Holidays assets | Alumni Valentine / New year assets | Tuyet | In Progress | Due 9 Feb