## WIP
· 3 Mar - 10 Mar 2026 | GCMC Weekly Report | Last updated 11 Mar, 02:10 ICT | High
Campaign (group) | Task | PIC | Status | Details | CustomFX
Shanghai Open Day 2026 | All static assets | Tuyet | In Review | Updated on 11 Mar
Shanghai Open Day 2026 | Prospecting videos | Trinh/Danh | In Review | Updated on 11 Mar
Shanghai Open Day 2026 | 20" Animation videos | Trinh | In Review | Updated on 11 Mar
Shanghai Open Day 2026 | Melburne To You video | Tran | In Review | In Review
Shanghai Open Day 2026 | Remarketing videos | Tran/Danh | In Review | 1st draft uploaded 10 Mar, waiting for review / resize
Shanghai Open Day 2026 | 2026 Open Day Style Guide | Trinh/Danh/Tran | Done | Approved and in use, Trinh won (this time)
Misc | Flashtalking 300 Program update | Danh | In Progress | Revision in progress, due 16 Mar
Domestic Open Day 2026 | Pre-production deck for approval | Danh/Tran/Eden | To Do | To do, due 13 Mar
Semester 2 mkt Campaign Phase 1 | Youtube videos | Danh | In Review | Updated on 11 Mar
Semester 2 mkt Campaign Phase 1 | Digital Display | Eden | In Review | In Review
Semester 2 mkt Campaign Phase 1 | Meta + EDM | Tuyet | In Review | In Review
CoBL Postgrad Business Campaign | Youtube videos + Reddit | Danh | In Review | In Review
CoBL Postgrad Business Campaign | Digital Display | Danh | In Review | 1st draft submitted 3 Mar. In Review
CoBL Postgrad Business Campaign | Meta + LinkedIn | Tuyet | In Review | 1st draft submitted 8 Mar. In Review
Misc | RMIT Trades Event - maps and design assets | Eden | In Review | 2/3 assets completed and approved. The rest in review.
Misc | INTON Foundation Studies Repurposing Video - Benson | Eden | In Progress | Due 18 Mar
Misc | SR H1 Career Practitioner Seminar 2026 | Eden | In Review | All assets in final review
Comms Holdays assets | Eid al Fitr Holiday EDM | Eden | In Progress | Working on R1 feedback
Comms Holdays assets | Holi 2026 eDM | Tran | Done | FA/WF sent
H1 2026 INTON Always On | China Always On - WECHAT & RED | Trinh/Tuyet | In Review | Assets updated on 10 Mar
H1 2026 INTON Always On | India Always On 2026 – PMAX creative asset | Trinh/Tuyet | Done | Assets updated