## WIP
¦ 18 Nov - 25 Nov 2025 | GCMC Design Team Weeky Report | Last updated 25 Nov, 00:25 ICT | Medium
Campaign (group) | Task | PIC | Status | Details
COP 2025 | Search PMAX (Art and Design) | Danh | In Review | Sent 13 Nov, in review
COP 2025 | P3 ¦ DOOH | Danh | In Progress | Working on extra assets (UltraWide)
MISC | Flashtalking (300+ programs) | Danh | To Do | Setting up datasheet
COP 2025 | COP Parent's guide PDF | Danh | In Progress | Due 26 Nov
COP 2025 | P2 ¦ VTAC Webpage | Eden | Done | Updated VTAC assets on 25 Nov
INTON BAU | Sem 1 2026 Foundation Studies Video 1 | Eden | Done | WF/FA sent 19 Nov
Alumni Breakfast Series | Presentation slides | Joanne | Done
Alumni Breakfast Series | Digital screen | Joanne | Done
Domestic SR Event | Career pathways posters | Joanne | On-hold | Awaiting content
Publications 2027 | IA spread design uplift concepts | Joanne | Done
Publications 2027 | IA spread design layout | Joanne | In Progress | Due 5 Dec
Publications 2027 | Editorial section design uplift | Joanne | To Do | Due 5 Dec
Publications 2027 | Program info review | Joanne | To Do
Publications 2027 | Ranking badge design V2 | Joanne | To Do
2026 Open Day | Teardrop banner | Joanne | To Do
2026 Open Day | Lanyard | Joanne | Done
INTON BAU | Chinese Alumni UGC video - Yiliang Zhang | Tran | To Do | Briefed on 25 Nov, due 5 Dec
COP 2025 | VTAC Art & Design short-form video | Tran | Done | WF/FA sent 14 Nov
COP 2025 | COP intervention: media and comms short-form videos | Tran | In Review | Videos updated on 25 Nov
INTON BAU | Sem 1 2026 Foundation Studies Video 2 | Trinh | Done | WF/FA sent 19 Nov
Brand extension logo | CoBL x3 | Joanne | Done