## WIP
¦ 2 Dec - 9 Dec 2025 | GCMC Design Team Weeky Report | Last updated 9 12, 00:25 ICT | High
Campaign (group) | Task | PIC | Status | Details
COP 2025 | COP 2025 Parents Guide PDF | Danh | Done | FA sent 8 Dec
COP 2025 | DOOH extra assets | Danh | Done | Sent 5 Dec
Misc | Guss Program uplift for 2026 intake | Danh | To Do | Briefed 4 Dec, waiting for reverse brief
Misc | RMIT Study Expo- January | Danh | In Progress | Revision in progress, due 12 Dec
Misc | INTON Christmas and new year design | Trinh | To Do | Briefed 5 Dec, extra asset brief to be added
Misc | Uni acronym challenge | Trinh | To Do | Due 19 Dec
Misc | Chinese Alumni UGC video - Yiliang Zhang | Tran | In Review | 1st draft sent 2 Dec
Misc | Chinese Alumni UGC video - Yiran Zhou | Tran | In Progress | Due 15 Dec
Misc | Aussie and international snacks reaction video series | Tran | To Do | Briefed 5 Dec, waiting for brief completion
Misc | Sri Lanka Intervention | Tran | Done | FA/WF sent 5 Dec
Misc | Popmart challenge video | Tran | To Do | Briefed 2 Dec, due 19 Dec
COP 2025 | Meta extra assets | Eden | Done
Sem 1 2026 | Sem 1 Career Connect TikTok | Eden | In Progress | Due 19 Dec
Sem 1 2026 | Sem 1 PG study tips TikTok | Eden | In Review | 1st draft sent 8 Dec, revision in progress
Sem 1 2026 | Sem 1 PG student IVs short-form videos (x3) | Eden | In Progress | Staggered delivery from 18 Dec to Mid Jan
Domestic SR Event | Career pathways posters | Joanne | On-hold | Awaiting content
Publications 2027 | IA spread design layout | Joanne | Done
Publications 2027 | Editorial section design uplift | Joanne | Done
Publications 2027 | Program info review | Joanne | To Do
Publications 2027 | Ranking badge design V2 | Joanne | In Progress | Due 10 Dec