## WIP
· 3 Feb - 10 Feb 2026 | TEST · GCMC Weekly Report | Last updated 10 Feb, 03:10 ICT | High
Campaign (group) | Task | PIC | Status | Details | CustomFX
INTON Holidays assets | INTON Valentine / New year assets | Danh/Trinh/Tran/Tuyet | In Review | All assets sent 9 Feb, in review
2026 INTON Open Days | 2026 INTON Event style guide | Danh/Trinh/Tran | To Do | In progress, due 25 Feb
RMIT Study Expo | RMIT Study Expo - printed assets | Danh | Done | Even passed before final revision
H1 Sem 2 | Semester 2 Marketing Campaign | Danh/Eden/Tuyet | To Do | Phase 1 due 4 March
H1 Domestic Always On | H1 Domestic Flashtalking 300 programs | Danh | In Progress | Due EO Feb 2026
Comms Holdays assets | Lunar New Year eDM GIF | Danh | Done | FA/WF sent 7 Feb
RMIT Trades Event | RMIT Trades Event - maps and design assets | Eden | To Do | Map asset done, waiting for printed assets info
H1 Domestic Always On | Domestic Always On 2026 | Eden | In Review | Concept selection in progress
Comms Holdays assets | Eid al Fitr 2026 eDM | Eden | In Progress | Due 27 Feb
Misc | SR H1 Career Practitioner Seminar 2026 | Eden | To Do | 2/6 assets done. The rest pending for more info
Comms Holdays assets | Holi 2026 eDM | Tran | In Review | Updated on 5 Feb, waiting for review
H1 2026 INTON Always On | H1 2026 Indonesia Always On – META & TIKTOK | Tran | In Review | 1st draft sent 9 Feb
Misc | x4 Aussie and international snacks reaction videos | Tran | In Review | All assets updated on 19 Jan
Misc | Popmart challenge video | Tran | In Review | Updated on 2 Feb
H1 2026 INTON Always On | H1 2026 China Always On - WECHAT & RED | Trinh/Tuyet | In Progress | Due 10 Feb
Comms Holdays assets | Ramadan Mubarak eDM | Trinh | In Review | Updated on Feb 6
Misc | Uni acronym challenge | Trinh | In Progress | Awaiting approval / review, due 6 Feb
H1 2026 INTON Always On | India Always On 2026 – PMAX creative asset | Trinh/Tuyet | In Progress | Due 13 Feb for static and 27 Feb for videos